## Slide 1: Kosrae State Energy Action Plan Update
Presentation from
KOSRAE UTILITIES AUTHORITY

## Slide 2
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS POWER IMPROVEMENT PROJECTS FOR POWER GENERATION 1.1 NEW POWER PLANT WITH TWO (2) 600 KW CONTRACTOR TO MOBILIZE 3 PHASE GENERATOR WITH ACCESSORIES BY FEBRUARY 2017 AND INDOOR SUBSTATION (JICA FUND) 1.2 POWER DISTRIBUTION SYSTEM UPGRADE IN SCHEDULED BY AUGUST 2017 LELU ISLAND. (JICA FUND) 1.3 UPGRADE OF OKAT UNDERGROUND POWER WORK TO START OCTOBER 2017 CABLES (JICA FUND)

## Slide 3
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 1.4 REPLACEMENT OF ONE (1) NON OPERATIONAL GENERATOR AT THE POWER PLANT WITH A NEW UNIT OF PROCUREMENT ON GOING 600 KW GENSET (WORLD BANK FUNDING) 1.5 UPGRADE OF FUEL STORAGE TANKS AT THE POWER PLANT FROM HOLDING CAPACITY OF 60,000 GALS. TO AWAITING FUNDING 100,000 GALLONS OF DIESEL.

## Slide 4
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 2. IMPROVEMENT PROJECTS FOR POWER DISTRIBUTION SYSTEM 2.1 CONDUCT GRID STABILITY STUDY ON SMART SUBSTATIONS WITH ENERGY STORAGE SYSTEM LEADING TO OPTIMIZING AND WAITING FOR FUNDING SYNCHRONIZING THE DIESEL GENERATORS OPERATION WITH RENEWABLE ENERGY SOURCES. (FUNDING WAS REQUESTED FROM GCF/ADB. 2.2 UPGRADE OF POWER DISTRIBUTION LINES AT THE FOLLOWING AREAS: A. DOUBLE CIRCUIT POLES FROM TOFOL TO PUHKUSRIK TRIANGLE B. PRIMARY POLES FROM WASR WASR, TAFUNSAK TO OKAT C. TAFUNSAK INNER ROAD EXTENSION WAITING FOR FUNDING D. UTWA WALUNG LINE UPGRADE E. CROSS ISLAND ROAD NEW POWER LINE F. OKAT MELO LINE EXTENSIION G. MALEM INNER ROAD INTERCONNECTION

## Slide 5
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 2. IMPROVEMENT PROJECTS FOR POWER DISTRIBUTION SYSTEM 2.3 Acquisition of major equipment to replace worn down equipment used for operations: A. Two (2) Lineman’s Bucket Truck B. One (1) Auger Truck ONE (1) LINEMAN’S TRUCK C. One (1) Tree Chipper Truck UNDER PROCUREMENT BY KUA; D. One (1) Backhoe/Excavator ANOTHER ONE (1) UNIT, LINEMAN’S E. One (1) Forklift, 3.5 tons TRUCK REQUESTED FROM W.B. F. One (1) Submersible Portable Pump 2.4 LED STREET LIGHTING PROJECT REPLACEMENT OF OLD AND INEFFICIENT STREET LED LIGHTS BEING PROCURED FROM LIGHTS WITH NEW AND LOWER WATTAGE LED LIGHTS. WORLD BANK FUNDING.

## Slide 6
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 2. IMPROVEMENT PROJECTS FOR POWER DISTRIBUTION SYSTEM 2.5 INSTALLATION OF 500 KVA PAD MOUNTED 3 PHASE TRANSFORMER UNIT BEING PROCURED FOR LUEN THAI FISHING VENTURE AT OKAT HARBOR. FROM WORLD BANK FUND. 2.6 ACQUISITION OF POLE MOUNTED TRANSFORMERS FOR FOR PROCUREMENT EMERGENCY REPLACEMENTS, HARDWARES, FITTINGS, FUSES, WIRES AND SPARES. 2.7 DISTRIBUTION TRANSFORMERS METERING; A PROGRAM TO MONITOR THE POWER LOADS AT THE INDIVIDUAL TO SECURE FUNDS POLE MOUNTED TRANSFORMERS TO VERIFY ACTUAL LOADING COMPARED TO INSTALLED TRANSFORMER SIZE. (RECOMMENDED BY KEMA)

## Slide 7
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 3. POWER PROJECTS FOR RENEWABLE ENERGY AND ENERGY EFFICIENCY 3.1 EXPAND THE CAPACITY OF THE SOLAR PV SYSTEM IN KOSRAE AWAITING FUNDING FROM FROM THE PRESENT CAPACITY OF 350 KW TO 750 KW. DONORS. 3.2 INSTALLATION OF ANOTHER 500 KW SOLAR PV SYSTEM PROPOSED BY PROPOSAL UNDER STUDY THE FSM NATIONAL GOVERNMENT TO THE JAPAN GOVERNMENT BY JAPANESE GOVERNMENT 3.3 FULL UTILIZATION OF CASHPOWER PRE PAID METERS TO PROGRAM IS ON FULL ALL KUA CUSTOMERS. IMPLEMENTATION AROUND 80 % COMPLETE. 3.4 UTILIZATION OF COMPACT FLOURESCENT LAMPS AND LED PROGRAM IS IN FULL LIGHTS TO RESIDENCES AND COMMERCIAL ESTABLISHMENTS. IMPLEMENTATION

## Slide 8
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 3. POWER PROJECTS FOR RENEWABLE ENERGY AND ENERGY EFFICIENCY 3.5 INSTALLATION OF SCADA PROGRAM FOR POWER PLANT TO BE CONSIDERED AND AND DISTRIBUTION SYSTEM INTERFACE/MONITORING. STUDIED AFTER THE CONSTRUCTION ( KEMA RECOMMENDATION) OF THE NEW POWER PLANT. 3.6 INSTALLATION OF KW DEMAND METER ON CUSTOMERS WITH NEEDS SPECIAL STUDY ON THE LARGE POWER DEMAND. FEASIBILITY OF THE PROJECT. BOARD DECISION IS REQUIRED AS REVISION OF POLICY WILL BE REQUIRED TO IMPLEMENT. 3.7 CONDUCT ENERGY EFFICIENCY AWARENESS PROGRAMS ON GOING PROGRAM TO MUNICIPALITIES AND SCHOOLS.

## Slide 9
HIGH PRIORITY PROJECTS
PROJECT PRESENT STATUS 3. POWER PROJECTS FOR RENEWABLE ENERGY AND ENERGY EFFICIENCY 3.8 CAPACITY BUILDING IN RENEWABLE ENERGY, PROGRAMS ARE COORDINATED WITH ENERGY EFFICIENCY SYSTEMS, ENERGY AUDITS, REGIONAL AGENCIES (PPA, SPREP, ALTERNATE ENERGY SYSTEMS, AND CONVENTIONAL SPC, ETC.) FOR APPROPRIATE ENERGY EFFICIENCIES. COURSES FOR ISLAND ENERGY PRACTIONERS. 3.9 DEVELOPMENT OF SOLAR PV SYSTEM WITH AN ENERGY PROGRAM IS UNDER DEVELOPMENT IN STORAGE FACILITY (FLYWHEEL SYSTEM), 1MW CAPACITY PARTNERSHIP WITH A US BASED ENTITY (INDIAN ENERGY ). 3.10 DEVELOPMENT OF OTHER RENEWABLE ENERGY SOURCES PROGRAM BEING COORDINATED WITH (WAVE, HYDRO, WIND, OTEC, BIO MASS, ETC.) OFF ISLAND ENTITIES (PPA, EU, ETC.)

## Slide 10
THANK YOU AND MORE POWER TO ALL